[image: image3.png]3

ae





MINISTRY OF INTERNATIONAL ECONOMIC RELATIONS 

Development and Aid Coordination Unit

HARMONISATION & ALIGNMENT
Enhancing Efficiency and Effectiveness of International Assistance in the Republic of Serbia
Progress Report

[image: image1.png]



Government of the Republic of Serbia

 February, 2005
CONTENTS
2Acknowledgements


31. Introduction


32. From DACU to ISDACON Network


53. ISDACON Information System


64. Harmonisation Activities in Serbia


95. Harmonisation – Ongoing and Planned Activities for 2005


126. Procurement, Financial Reporting and Audit


13ANNEX 1- ISDACON Scheme


14ANNEX 2 – Joint Pilot Project towards More Effective Reform Implementation



ANNEX 3 – DACU Action Plan-draft………………………………………………………………16
ACKNOWLEDGEMENTS
The HARMONISATION & ALIGNMENT - Enhancing Efficiency and Effectiveness of International Assistance in the Republic of Serbia was prepared by the Development and Aid Coordination Unit (DACU) team of the Ministry of International Economic Relations of the Government of Serbia. 

The document was prepared, edited and reviewed by the DACU team, consisting of Mila Marinkovic (Task Manager, who led the preparation of the overall document), and the following Consultants: Aleksandra Milenkovic-Bukumirovic, Maja Milenkovic and Mico Basara. 

The team benefited from guidance received from Lars Andre Skari (Adviser to the Poverty Reduction Strategy Implementation Focal Point in the Deputy Prime Minister Cabinet). Comments on the document were received by Robin Milton, Social Development Adviser, Europe and Central Asia Department, DFID) and Alison Evans (Consultant).

The report was prepared under the overall supervision of Gordana Lazarevic (Assistant Minister) and Marija Sijan (Head of DACU). 

1. Introduction

1. The purpose of this Progress Report is to present the current harmonisation and alignment efforts of the Government of Serbia (GoS). It presents country specific considerations linked to the harmonisation agenda and outlines some of the opportunities and plans for the future. 
2. The GoS recognises that the harmonisation of policies, procedures and practices of donors and development institutions, aligned with the development priorities and systems of the GoS, as well as the principles of the Rome Declaration, is necessary to improve the effectiveness of development assistance. 
3. By the Government of Serbia Decision, adopted on 27th of May 2004, Development and Aid Coordination Unit, of Ministry of International Economic Relations (MIER), is co-ordinating and facilitating donor harmonisation process in Serbia. Harmonisation in Serbia has been initiated by MIER/DACU, on the basis of Rome Declaration. 
4. MIER/DACU started with harmonisation efforts in Serbia through strengthening of responsible institutions and development of mechanisms within the GoS necessary to implement the harmonisation agenda. At the same time, MIER initiated a series of informal consultations and negotiations with donor representatives in Belgrade in order to identify the areas for harmonisation and, consequently, implement concrete harmonisation activities in those areas.
2. From DACU to ISDACON Network
5. From the beginning of the transition process, the GoS showed political commitment in using provided international assistance effectively in order to speed up the reforms. To this end, the focal point for coordination of international support to Serbia, the Development and Aid Co-ordination Unit (DACU) was established within MIER in November 2000 and tasked with promotion of national priorities through close cooperation with donors and development partners
. 
6. As soon as the DACU was established it recognised the crucial role of line ministries, and started an intensive day-to-day cooperation with them. The contacts varied from personal assistants, junior experts to Deputy Ministers. This joint work included the following:

· Defining priorities of different line ministries/sectors; 

· Drafting and collecting specific projects that were to be financed by external assistance;
· Defining the content of various sector documents, as well as overall GoS strategies; 

· Organising donor meetings; 

· Fulfilling everyday tasks and exchanging information related to international cooperation.
7. This cooperation was initiated ad hoc, as a result of then non-existent institutional procedures, or memory related to the management of international assistance. Both DACU and staff in line ministries were tasked with activities that, among other things required experience, expertise and sound institutions. 

8. Over time, both the capacities within line ministries and the need for more systematic approach to the management of assistance within sectors grew, which resulted in the establishment of units dealing with international cooperation. These units, usually headed by Assistant Minister, mostly applied the model used in the DACU, i.e. a staff member was in charge of following a specific donor/project related activities. 
9. ISDACON (Inter Sectoral Development and Aid Co-ordination Network (ISDACON) was formally established through the Government Decision from September 2003. The scope of work of the ISDACON Network was defined on the basis of the activities and tasks already performed by DACU and line ministries, which were mentioned earlier. The purpose of the Network is to facilitate communication and the flow of information on development and international assistance within the GoS, and to plan proactively in order to ensure that aid complements reform efforts towards EU integration and Poverty Reduction Strategy (PRS) implementation. The establishment of ISDACON Network provided an institutional base for inter-sectoral cooperation within the GoS, i.e. horizontal function for the management of international assistance. ISDACON consists of representatives from all line ministries (operational level) with the scope and capacity to proactively programme, coordinate, manage and monitor international assistance (See more in Annex 1 – ISDACON Scheme). 

10. Furthermore, MIER/DACU initiated the establishment of Steering Committee for Development and Aid Co-ordination (SC). SC has the official mandate to draw attention to policy gaps, define cross-sectoral priorities, as well as to identify the gaps for international financing. Members of the SC are: Prime Minister, Minister of Finance, Minister of Labour and Employment, Minister of International Economic Relations and Minister of Trade, Tourism and Services. 

11. In March 2004, the new Government of the Republic of Serbia took office. With the change of the Government, the ISDACON structure also changed. This imposed an additional challenge to the DACU, namely:

· New Government had to be informed of the importance and purpose of such a network, in particular its cross-sectoral function;
· New ISDACON members had to be acquainted with the ISDACON activities and its manner of functioning.

12. During September 2004, in a relatively stable political environment, having developed the ISDACON Information System (IS) over the previous period, and with the harmonisation and alignment agenda instigated, DACU started with a more systematic and in-depth approach to the development of ISDACON. This approach included the following:

· Training for ISDACON members in active use of the ISDACON IS;
· Enabling the ISDACON members to proactively improve the content of ISDACON IS, through input of data, contribution of documents, news, promotion, etc.;
· Empowering the ISDACON members to anchor the activities related to the management of international assistance;
· Training of donor representatives in active use of the ISDACON IS;
· Examining possibilities for joint donor support to sectors/programmes/projects;
· Launching the Sector Support concept (SSp), with the idea of harmonising activities of different donors within a sector;
· More intensive and harmonised manner of cooperation with Governmental teams and offices that also deal with inter-sectoral issues;
· Further strengthening of existing institutional infrastructure (ISDACON) from the aspect of poverty reduction and European integration.

13. In order to further joint efforts by the ISDACON Network, DACU, SEIO and PRS Implementation Unit, a four-day retreat was organised in December 2004. In line with the bottom up approach, this retreat was the first initiative which gathered operational level representatives of line ministries/units/offices who set out the background, current situation, as well as challenges that lie ahead the work of Governmental institutions. In the light of harmonisation initiative in the very Government of Serbia, all participants concluded that their institutions were facing common problems, which highlighted the need for a joint approach to resolving the issues through public administration reform. 

3. ISDACON Information System
14. In order to support ISDACON activities, DACU developed an integrated ISDACON information system
. This information system has the capacity to support foreign aid management process in all its phases. It has an adaptable module for prioritisation and evaluation of project proposals, it manages financial and descriptive data about individual projects and donations, and at the same time it acts as a common data storage and information source for all stakeholders. 
15. With four years of historical data already in the system, ISDACON I.S. contains a unique set of reports which present and analyse implemented foreign assistance, as well as information on activities undertaken by the GoS to facilitate the implementation of international support. During the development of this system, procedures of communication among institutions of the GoS were researched, as well as the procedures of communication between the GoS and donor community. 
DACU invites line ministries and donor agencies to work in partnership in order to further upgrade and promote the ISDACON IS. This partnership will ensure shared responsibility of all relevant stakeholders for validity of data. Special attention will be devoted to improvement of the accuracy as well as consistency of the data in the system. Furthermore, the system can be adapted to the specific needs of stakeholders.
16. Apart from the data related to the programmes and projects financed through international assistance, the information system contains various information and references based on DACU four-year experience in the field of international cooperation in the Republic of Serbia. The ISDACON IS covers most of the aspects of international cooperation, providing latest news, sets of different documents, reports, project proposals and much more. 
17. DACU prepared a unique set of Donor & Sector ID cards (featuring donor/sector profile, strategies, procedures, overview of programmes and projects by donor/sector, as well as the summary of experiences with individual donors/sectors so far). 
18. ISDACON IS is open to broad public, ensuring transparency of the reform processes in the Republic of Serbia, supported by international partners. This system represents a pioneer effort in the establishment of an efficient horizontal communication between all relevant Governmental institutions. Consequently, as a joint knowledge base and flexible information management tool, which can be customised and expanded, ISDACON IS is able to meet the needs of different stakeholders in a dynamic environment of public administration in the Republic of Serbia. 

ISDACON IS and the process model behind it will serve as a backbone of the harmonisation process, as well as the knowledge base and information management centre for the harmonisation initiative in the Republic of Serbia. Therefore, the Government of Serbia wants to ensure that all donors and line ministries start using ISDACON Information System by April 2005. This will secure further administration reform and the development of cross-sectoral functions within the Government. 

4. Harmonisation Activities in Serbia

4.1 Background 
19. Due to the shift from emergency and humanitarian to medium and longer-term development assistance, the process of planning and implementation of international assistance has become more complex and challenging. Currently, there is a growing awareness in the donor community in Serbia that the totality and wide variety of donor requirements and processes for preparing, delivering, and monitoring development assistance is generating unproductive transaction costs, drawing down the limited capacity of the GoS. Harmonisation process will enable the GoS to use the provided international assistance more effectively, which will ensure speeding up of the reform process.
20. At the Donor Coordination Meeting held on 28th of May 2004, MIER/DACU presented a draft document Donor Harmonisation Framework for Serbia (DHF). DHF was prepared by DACU, presenting general harmonisation principles the GoS and donor community should agree upon. This document was a starting point in the development of this Progress Report and The Road Map for Sector Support. 
4.2 The partnership 
21. MIER/DACU decided to develop the harmonisation process in partnership with line ministries, other government institutions and donor representatives. Therefore, MIER/DACU started formal and informal consultations with all stakeholders in the process. Although the consultation process is time consuming, it will ensure smoother implementation at a later stage.  

4.2.1 DACU in Partnership with Donors 

22. The first round of consultations with donor representatives, conducted by MIER/DACU during the period of June-October 2004, identified a critical mass of donors/IFIs interested in furthering the harmonisation agenda
.
23. The general response to MIER/DACU harmonisation initiative is positive. There is a willingness among donors to participate in a dialogue aimed at identifying concrete steps for harmonisation. Representatives in Belgrade highlighted that harmonisation initiative has to be fully supported by their headquarters. MIER/DACU also observed that some of the donors did not show a great understanding of the harmonisation process. Very often they were confusing it with coordination and exchange of information. Therefore, MIER approach so far has been to discuss the existing problems, trying to jointly identify possible solutions. It has been concluded that some of these problems can be addressed by harmonising “the way of working together”. As a result, a need for improvement in cooperation has been expressed in some of the following areas
: 

Programming
· To further strengthen, harmonise and standardise the process of programming of international assistance: aligning planning cycle of donors with planning and budgeting cycle of ministries; to strengthen the link between programming of international assistance and the GoS planning and budgeting process; to streamline planning and implementation of development assistance in accordance with the following documents: European Integration process (EIp), Poverty Reduction Strategy (PRS) and Serbia on the Move, as well as with sectoral strategy papers; 

· To further decentralise/delegate decision making process from the headquarters to the offices in Belgrade.
Pilot initiatives - Sector Support
· To identify sectors for pilot initiatives, as well as a lead donor per sector;
· To initiate sector reviews.
Knowledge management
· To harmonise and implement procedures for foreign aid management; 

· To establish a document centre;
· To organise donor and sector harmonisation meetings on a more regular basis.
Reporting, monitoring & evaluation

· Minimum criteria and reporting requirements to be defined and standardised according to the needs of the GoS;
· Government representatives to participate in project/programme evaluation, together with respective donor; 

· Analytical work for a donor country strategy documents to be carried out jointly, consulting other donors performing the same process in advance;
· Defining criteria and guidelines for successful replication of pilot projects. 
Procurement activities
· To establish a joint donor and ISDACON working group that will identify harmonisation initiatives aimed at easing the burden of different audits, procurement and financial reporting requirements;
· To look into the possibility of developing sustainable solutions for integrating externally funded Project implementation units/project co-ordination units into the ISDACON Network.
24. MIER/DACU started with the second round of consultations with donor representatives in October 2004. The aim is to further promote the harmonisation initiative in Serbia (especially with donors that have not been included in the process from the very beginning). At the same time, DACU is spreading the awareness of ISDACON IS, discussing more technical details and specific needs of different donors
.
25. As of October 2004, DACU started organising harmonisation meetings with donor representatives on a more regular and more proactive basis
. In general, the objective of these meetings is to improve the effectiveness and impact of assistance provided to Serbia by: 
· Ensuring a more regular flow of information; 
· Reviewing the link between the EI process/PRS implementation and draft strategies prepared by development partners; 
· Enhancing the focus of the draft strategies/programmes in order to avoid potential overlap and utilise possible synergies; 
· Identifying lessons learnt and best practices. 
During the meetings, participants are able to discuss cross-cutting problems and challenges that influence both the programming and implementation of international assistance, as well as the opportunities for harmonisation of procedures. Ensuring the participation of representatives of the Ministry of Finance, the harmonisation meetings are aimed at strengthening the link between programming of international assistance and the GoS Budgeting process, both of which should be aligned with the EIp and PRS. 
26. DACU has recognised a unique opportunity to launch a dialogue with its key international development partners, at a moment when European Commission (EC), the World Bank (WB) and USAID started preparing multi annual strategies in the form of Multi-Annual Indicative Programme (MIP) 2005-2006, Country Assistance Strategy (CAS) 2005-2007 and Strategy for assistance to Serbia, respectively. Therefore, DACU organised an informal working meeting on 13th October 2004, between the key development partners (EC, UN, USAID and WB) and key Government officials (Deputy Prime Minister, Minister of Finance and MIER representatives). The meeting provided an opportunity to strengthen the link between programming of international assistance and the GoS priorities and the budget process for 2005. 
27. The Meeting on Harmonisation held on 9th November 2004, promoted harmonisation efforts in the Republic of Serbia with the aim of initiating questions and suggestions by different stakeholders. MIER presented the concept and current status of the harmonisation process and outlined opportunities and plans for the future. 

28. MIER/DACU ensured participation in Second High-Level Forum on Harmonisation and Alignment for Aid Effectiveness, in Paris in February 2005. This is the opportunity for the GoS to present to the world-wide public harmonisation initiative and the ISDACON IS, as a tool for harmonisation in Serbia. Moreover, MIER/DACU will exchange its experiences, lessons learnt and best practice in this field with other developing countries.
4.2.2. DACU in Partnership with Line Ministries  

29. In the course of the consultation process donor representatives also identified a bottleneck within the administration of the GoS. Therefore, DACU started with the intensive training of ISDACON members, as of August 2004, in order to strengthen the capacities of the GoS related to programming, implementation and monitoring of international assistance as well as to the donor harmonisation function. For the success of harmonisation activities it is essential to ensure that ISDACON Network is fully operational. The planned strengthening of the ISDACON Network, together with the development of a more comprehensive/holistic and long term policy framework represent the basis for the GoS efforts to promote harmonisation of international assistance and Government’s own priorities, strategies and delivery mechanisms. Within these activities, DACU will actively promote the use of ISDACON IS both by the GoS and the donor community representatives. DACU trained 70% of line ministries by the end of November 2004 and the other 30% will have been trained by April 2005.
30. Moreover, MIER has initiated discussions with different line ministries
: During the consultation process line ministries have identified a number of areas in which they would like to see significant improvements. In most cases, identified problems were the same ones identified by donor representatives. Some of the requirements are as follows:
· To standardise the process of programming of international assistance; 

· To organise donor and sector harmonisation meetings on a more regular basis;
· To be consulted in advance, basically when donors are preparing their strategies, programmes and/or projects. Very often, donors just “appear” with prepared project proposals and already defined ToRs, names of consultants etc.;
· To systemise all available information about donor activities in a sector, best practices and lessons learnt, etc.;
· To improve reporting system used by donors (implementing agencies). Reports are long and donor driven (designed for the donor specific needs);
· Avoid duplications and overlapping of feasibility studies performed in the same area;
· Speed up a rather slow decision making process (priorities may change very fast when  it comes to the specific projects);
· In some cases consultants seconded to the ministries do not have understanding of the in-country details needed to adequately fit their policy recommendation in the country specific circumstances;
· Avoid proliferation of preparatory work on specific donor operations. 
5. Harmonisation – Ongoing and Planned Activities for 2005
5.1 - Overall Framework for Reforms
31. The Government of Serbia realises that existence of an overall strategic framework with clear development priorities is a precondition for effective planning and implementation of reforms and for successful harmonisation and alignment leading to improved effectiveness of development assistance. 
32. An effective public administration is a starting point for the development and implementation of such a strategic framework, hence the GoS is committed to improving the efficiency and transparency of administration. Nevertheless, policy-making systems and processes remain fragmented, with low inter-ministerial coordination capacity and independent ministries with underdeveloped policy capacity. This situation, together with fragmented external demands for specific reforms and initiatives, has resulted in multiple and partly overlapping cross-cutting strategies that are not placing enough emphasis on complementarities, compatibilities and commonalities. 
33. Serbia’s development priorities are mainly defined by two pillars, EIp and the PRS implementation. In order to maximise the impact and effectively implement the overall reform agenda, it is significant to ensure integration and consolidation by both linking the EIp and PRS to each other, as well as to relevant cross-cutting processes
 and sector strategies. Furthermore, to promote effective implementation of reforms it is necessary to ensure that the budget process and programming of international assistance are fully aligned with the above mentioned development priorities. 

34. The Government of Serbia is taking steps to resolve the aforementioned situation both on operational and strategic level: 
· PRS Implementation Unit, MIER, SEIO and MoF, with the involvement of Secretariat General (GS), have launched a joint project for five to six key sectors, with the purpose to operationalise these strategies through a process of developing one comprehensive Plan of Action per sector, that will be used in budget process, programming of international assistance, monitoring and evaluation, etc. 
· Furthermore, key Government institutions are currently discussing the best methods for consolidating different strategies into one overall strategic development framework over the medium term. Such a strategic framework or development plan is also a precondition for efficient use of pre accession funds

35. The process of drafting comprehensive plan of actions for each of the pilot sector will be designed and implemented based on a decentralised / bottom up approach aimed at developing strong ownership within responsible line ministries A common framework used on a daily basis by SEIO, PRS Implementation Unit, DACU and MoF would increase the leverage and the impact of overall reforms. Such a consolidated approach would motivate line ministries to use this framework to improve both their planning processes and day-to-day management of the reforms, budget resources and international assistance. Additionally, this initiative will support policy coherency and reduce the burden on the line ministries, since the number of reporting requests from co-ordinating central government bodies will be reduced. ISDACON IS, a web based tool will support dissemination of information, regular updating and reporting. This will ensure that the Plan of Action(s) becomes a dynamic and effective instrument that can be used as a base for allocation of national resources and international assistance, as well as monitoring and evaluation. To take advantage of possible synergies it is critical that planning processes are aligned with the budget process. For more information regarding the “joint project” see enclosed Annex 2.

5.2 ISDACON IS – Tool for the Harmonisation Process
36. DACU will upgrade the existing logistic support 
· Internally, within MIER, logistic support to donor harmonisation process will be provided through services of ISDACON IS, including shared data storage, mail and Internet, as well as document and process management - MS Project and MS Sharepoint Portal (ongoing activity);
· On the sectoral level, harmonisation of the GoS’ procedures will be supported through ISDACON IS (ongoing activity);
· On the donor level, the process of harmonisation of donor procedures will be directly supported through ISDACON IS (ongoing activity); 

· Externally, on the central level of the GoS, ISDACON IS will be connected to the information system of the Treasury Department and other information sources in the Government of Serbia related to EU SAP and PRS implementation. Therefore, donor harmonisation will be synchronised with related processes (ongoing activity);

· Externally, towards local self-government authorities, ISDACON IS will become available to local self government authorities, with the aim of supporting the process of decentralisation and delegation of programming, implementation and monitoring of international assistance. This will be a joint activity of DACU and the Standing Conference of Cities and Municipalities. (launching planned for 2006).

· Regionally, towards neighbouring countries ISDACON IS will be promoted (See more under paragraph 39)
· World-wide, towards other developing countries, ISDACON IS will be presented at the Second High-Level Forum on Harmonization and Alignment for Aid Effectiveness, in Paris in February 2005.
5.3 Legal / Institutional Framework
37. DACU identified a wide range of general activities in order to create the legal framework for the harmonisation process. The initiatives/activities (will) include:

· Further upgrade of the Harmonisation Plan of Action with specified areas and activities for harmonisation efforts, based on the country specific context, Progress report, as well as on areas for harmonisation identified through the consultation process with donor representatives (Annex 3)

· Liaising between the EU, PRS and other overall and inter-sectoral agendas and permanent improvement of ISDACON capacities, in order for it to become a strong focal point within the GoS for the harmonisation process (ongoing activity).
· Preparation, signing and beginning of implementation of Memorandum of Understanding (September 2005). MoU will be a “dynamic document” in two respects: 

· the contents may change in the light of experience, and 

· additional signatory partners may choose to sign the Memorandum of Understanding (MoU) at a later stage

· Establishment of the Harmonisation Group. The donors, signatories of the MoU, will become the members of the Harmonisation Group. Harmonisation Group will periodically review the implementation of the HF. Along with MIER/DACU representatives, two donors will be responsible for ensuring the MoU implementation, on a rotating basis. The specific Terms of Reference will be developed by DACU and the lead donor for harmonisation process (September 2005);
· Establishment of the Sector-Donor Group (SDG) for SSp pilot sectors (more information available in the document: The Road Map for Sector Support) (July 2005);
5.4 External Cooperation

38. Internationally, DACU seeks cooperation with other developing countries with more advanced harmonisation process in order to share experiences and lessons learnt. DACU will insure the participation in working tables and conferences organised to discuss the harmonisation agenda (March 2005).  

39. Regionally, DACU will improve the cooperation with neighbouring countries in order to start sharing experience, best practices and lessons learnt in the field of international assistance and harmonisation across the region. As a starting point, MIER/DACU invited the representatives of the neighbouring countries to take part in the meeting on harmonisation with the “country observer” status. This cooperation will be further discussed bilaterally. DACU is planning to organise informal bilateral consultations, round tables, as well as visits to governments and units/ministries which deal with international assistance (March 2006). 
5.5 Sector Support 

40. As a result of consultations with line ministries, retreat organised for ISDACON members in December 2004, DACU experience and experiences of other developing countries DACU prepared discussion paper – The Road Map for Sector Support. This document was finalised in February 2005 and it is currently disturbed widely for further consultations. For more details please see the document-The Road Map for Sector Support (ongoing activity).

41. DACU will start organising regular ISDACON retreats (twice a year) in order to secure capacity building of ISDACON Network (started in December 2004, ongoing)
42. DACU will launch a series of sectoral meetings in cooperation with line ministries, on a more regular basis and focused on specific sectoral programmes. The aim is to move towards a more consolidated policy and programme discussion at sector or theme level (Starting in September 2005).

DACU seeks international assistance to support Sector Support implementation, capacity building of ISDACON Network, as well as its regional and international initiatives.
6. Procurement, Financial Reporting and Audit
43. The World Bank have expressed a great interest in harmonisation of donor activities in the areas of procurement, financial reporting and auditing. MIER recommendation is that on behalf of the Government, Public Procurement Office (PPO) should take the lead in harmonisation efforts in the field of procurement. In addition to the positive effects of harmonisation, this will strengthen the capacities of the already established institution. External assistance is needed for the successful preparation and implementation of the harmonisation process in the procurement area. MIER will facilitate this process and will include a PPO representative in ISDACON Network. In addition to this, PPO requirements will be included in ISDACON IS.

44. The PPO is set up as an independent governmental agency with the mission to help the establishment of sound procurement procedures and practices ensuring that the public funds are spent in an efficient and transparent way, thus complementing government's overall efforts in combating corruption
. 
45. Since 2001, a number of Project Implementation Units/Project Co-ordination Units have been established with the purpose to implement projects funded by WB, EIB and EBRD. As these units are operating and/or are organised in different manners there is a need to investigate possible harmonisation advantages from merging these units with the ISDACON. In this context, a specific focus should be placed on financial reporting and auditing, in addition to already mentioned procurement. 
46. MIER will strongly encourage the WB to take the leading role within the area of procurement and provide support to PPO.
47. An initiative looking into the aforementioned area is already ongoing in the Agency for Deposit Insurance, Rehabilitation, Bankruptcy and Liquidation of Banks (BRA). This initiative is exploring possible harmonisation activities within the reform of Financial Sector, with a specific focus on privatisation of banks and regulatory reforms. 
ANNEX 1- ISDACON Scheme 
[image: image2.png]Inter Sectorial Development and Aid Coordination Networl -
1SDACON

Seering Commites for Ceuecprmart ana i
Cooraratian
Chaiedbythe i Wi
Gepi Pima niter
IvimrofFrancs
Minte Trate. Toura 3 Serices

iz ol B sons
e reie Rl {ense. |

Soncon
Representatives of the Departrents for
Intermational Cooperation / European
Integration of the Ministries of the.
Goverrment of Sertda

SEG Sitin Eipean egtin Ties
PRSP —Porsty Reduaon Srtegy Paper il smetaon Taam
Dac peelopmert and £d Cordratn Lt





ANNEX 2 – Joint Pilot Project towards More Effective Reform Implementation 

The project has been initiated by PRS implementation focal point, Serbian European Integration Office, Ministry of Finance and Ministry of International Economic Relations and in cooperation with Secretariat General and Ministry for Public Administration and Local Self-Government. 

This pilot project aims at tackling a number of the above-mentioned challenges by developing capacity and tools with a threefold purpose:

· Strengthening policy and planning capacity within line ministries through the development of comprehensive and realistic sectoral plans of action that would bring together all reforms and strategies within the relevant sector into one joint reform framework, serving as a monitoring and evaluation tool, and in line with Budget and international assistance programming requirements; 

· Improve efficiency of the overall reform process by consolidating and bringing together activities and networks across the Government that are initiated and managed by Serbian European Integration Office (SEIO), Poverty Reduction Strategy Implementation Focal Point (PRS IFP), Ministry of Finance (MoF), Ministry of International Economical Relations (MIER) and potentially Secretariat General (SG) of the Government;

· Provide conditions and develop tools and systems for the future strengthening of the central co/ordination role of the Government.
A joint reform framework created through this process would reduce the burden on the line ministries and the number of reporting requirements from co-ordinating central government bodies. 

This 10-month pilot project which is targeting SG, SEIO, PRS, MoF and MIER, as well as five Ministries in the GoS is designed to maximise learning effect within the participating organizations, based upon a “learning by doing” approach. This initiative aims at supporting the development of a comprehensive plan of actions for five sectors,  (including two sectors already identified as possible pilots for SSp).
The project aims to develop tools and methodologies that, at a later stage, can be used across all sectors. If successful, this pilot project will be followed by a larger project targeting more sectors/Ministries. 

Successful implementation of the project will result in the development of approaches and methodologies for delivery of international assistance which are more effective and efficient than the ones used currently. 








































� In order to ensure capacity building for the aid coordination function within the GoS, the United Kingdom Department for International Development (DfID) has been supporting a part of the DACU since its establishment.





� Following the feasibility study performed in June 2001, the establishment of the ISDACON IS was initiated. The support for this process has been provided by Swedish International Development Agency (SIDA) ever since.


� MIER/DACU met the following donor representatives in Belgrade: DfID and the Netherlands (7th June), SDC (25th June 2004); DfID (28th  June); EAR ( 2nd  July); WB (6th  July); CIDA (7th July); SIDA (8th July); DfiD (14th July); UNDP (15th  July); KPMG (23rd July); WB (3rd September); Germany (7th September); CIDA (24th September); DfiD (5th October), USAID (22nd October)


� Please note that not all donors supported all listed areas/proposals


� In the second round, so far, MIER/DACU met: USAID (22nd October), CIDA (25th October); Denmark (28th October), DfID (29th October); EBRD (29th October); SIDA (29th October), Denmark (24th January 05); Czech Republic (16th February) Austria (16th February 05); UNICEF (10th February 05); UNDP (17th February 05)


� In the previous period, as a part of its coordination activities, DACU was organising donor coordination meetings twice a year presenting the current status of international assistance (Reports on International Assistance to the Republic of Serbia) and highlighting main recommendations, lessons, best practices and suggestions for the future.


� Ministry of Health, Ministry of Justice, Ministry of Interior, Ministry of Public Administration and Local Self-Government, Ministry of Capital Investments, Ministry of Economy


� Millennium Development Goals, National Action Plan for Children, Roma Strategy; Sustainable Development Strategy, Employment Strategy, etc.


� The aim of the PPO is to promote knowledge and understanding of Public Procurement Law. The foundations of a modern system of public procurement in Serbia were laid on 13th July 2002, when the Public Procurement Law was passed. 








13
2

[image: image3.png]_1170403962.bin

_1170403732.bin

